## Sheet1
|  |  |  | January | Feb | Feb | Feb | Feb | Mar | Mar | Mar | Mar | April | April | April | April
|  |  |  | 1/30 - 2/5 | 2/6 - 2/12 | 2/13 - 2/19 | 2/20 - 2/26 | 2/27 - 3/5 | 3/6 - 3/12 | 3/13 - 3/19 | 3/20 - 3/26 | 3/27 - 4/2 | 4/3-4/9 | 4/10-4/16 | 4/17-4/23 | 4/24-4/30
Vision: | Recreate Zork Adventure in 3D
| Tasks: | Difficulty: | Status:
| Fix issues with Mac development | 2023-08-13 | Done | Start | First interactions | Troubling point in time | Changed to windows part | Solved | Solved | Solved | Solved | Solved | Solved | Solved | Solved | Solved
| Extended research to inventory and hotbar | 2023-03-05 | Mostly complete |  | Start | Reviewing, nyic | still reviewing/starting implementation | Starting | inventory screen, no items | Mostly Complete | Mostly Complete | Mostly complete | Mostly complete | changing to hotbar and holding item | holding item, no hotbar as uneccesary visual clutter for the time being | Items can be held and seen in inventory screen
| Extended research into QTE | 2023-05-08 | Started |  | Start | Reviewing, nyic | still reviewing/starting implementation | still reviewing | still reviewing | still reviewing | Still reviewing | Still reviewing | Still reviewing | Starting implementation | Implementation on hold | Scrapped, too much time, not enough time to do it in
| Build World/1st Level Set | 8-13/5-8 | Demo status |  |  |  | getting started | small segment for demo purposes | small segment | segment ready for demo | Still at 1st demo state | 1st demo | 1st demo | 1st Demo | Terrain created, some holes patched | Terrain generated, holes patched, visuals applied
| Ladders | 2023-02-03 | Done* |  |  |  |  | Started | Started | Mostly complete | Mostly complete | minor problem and solutions identified | Solution implemented, but not original intent | ditto from last week | ditto from last week | Alternate solution in place
| Item interaction | 2023-03-05 | Done* | [5 empty] | started | mostly complete | Mostly complete | Mostly complete | Mostly complete | changing to raycast/proximity interaction | change nyi | Raycast proxy in place, works on picking up items and world interactions
| Lighting & Mechanics | 2023-03-05 | Mostly complete | [5 empty] | lighting mostly solved | most lights implemented not mechanics | Lighting implemented, mechanics separated | Lighting Done | Lighting Done | moving logic to player | logic moved, some exec problems | Completed, lights can be turned on and off and affect Grue logic
| Getting eaten by a Grue | 2023-03-05 | Mostly complete | Mar: Separated from lighting; Mar: initial review of mechanics; April: Mostly complete logic circuit, will need tweaking; April: moving logic to player; April: logic moved, some exec problems; April: Grue logic completed, warnings of being eaten displayed
| Generate AI | 2023-05-08 | Started | Mar: First NPC entity created, no actual AI yet; Mar: ditto from last week; April: ditto from last week; April: ditto from last week; April: ditto from last week; April: Scrapped, too much time, not enough time to do it in
| Using items | 2023-05-08 | Logic started | April: Started, most logic done; April: NYI; April: Completed with current item and world set